Sample Settlement week Action Plan Timeline

This is a sample form.  Courts will need to modify it to match their protocols, procedures and timelines.

☐ 	Settlement week dates - at least 5-6 months prior

- Court selects settlement week dates

- Judges, Magistrates, Court Administrators, and courtroom staff notified of selected settlement week dates

- Settlement week coordinator appointed

- Court and coordinator review and update action plan

☐ 	Save the Date Notice - 16 weeks prior

- Coordinator sends settlement week save the date notice to private mediators

- Coordinator sends save the date notice to all courtrooms

- Coordinator sends save the date notice to local Bar Association and attorney groups

- Coordinator shares statistics from previous settlement weeks with Judges and Magistrates

- Coordinator asks Judges and Magistrates to begin considering cases for settlement week referral

☐	Update Entries/Orders - 15 weeks prior

- Coordinator sends Court Administrator and Judges draft templates for Orders / Entries

- Upon approval, Coordinator turns Orders / Entries into fillable PDF forms

☐ 	Spreadsheets and Staff Instructions - 14 weeks prior

- Coordinator creates main spreadsheet, mediator availability spreadsheet, and daily room assignments spreadsheet

- Coordinator reviews preliminary settlement week action plan with staff

☐ 	Promotion Preparation – 13 weeks prior

- Coordinator orders posters, flyers, and any other promotional materials from print shop

☐ 	Mediator Recruitment - 12 weeks prior

- Coordinator emails private mediators about availability

- Coordinator reviews mediator applications

- Coordinator enters responses on mediator availability spreadsheet

☐ 	Official Announcement – 8 -12 weeks prior

- Send settlement week announcement to all Judges, Judicial Assistants, Bailiffs, Staff Attorneys, Magistrates, Court Officers, Court Administrators, Public Information Coordinator and Dispute Resolution Department

- Send settlement week announcement to local Bar Association and attorney groups

- Hang posters around courthouse, distribute flyers

- Provide courtrooms with referral order/entry, courtroom checklist, and litigant handout

- Ask Public Information Coordinator to create and post announcements on Court’s social media platforms

- Ask Judges and Magistrates to refer cases they believe are appropriate for settlement week

- Invite attorneys to submit cases they would like to have considered for settlement week mediation

☐ 	Mediator Selection – 8 – 10 weeks prior

- Coordinator provides court with list of qualified mediators who are interested in mediating during settlement week

- Coordinator notifies mediators of acceptance / non-acceptance

- Mediators notified about settlement week training for mediators (if any)

☐ 	Process Mediation Referrals – as directed by Court

- Coordinator and staff receive and process referrals from attorneys and parties

- Coordinator provides list of referrals to Judges / final decision makers

☐ 	Prepare Mediation Schedule – 7 - 10 weeks prior

- Prepare mediation schedule

- Enter case information on spreadsheets when received

- Inform attorneys, parties and mediators of mediation dates and times (information may be provided in a Court Order or in a scheduling letter)

☐ 	Create Final List of Cases to be Mediated – 3 - 4 weeks prior

- Enter case information on spreadsheets.

- Send list to Judges and Magistrates

☐ 	Send Information and Forms to Mediators – 2 - 4 weeks prior

- Send mediators forms, protocols, and outcome notice templates

- Send mediators Court Orders or other information about assigned cases

☐ 	Supplies Check – 2 weeks prior

- Take inventory of refreshments: snacks, water, coffee, napkins, etc.

- Order office supplies including pens, tissues, wipes, etc. as needed

☐ 	Reminders – 1 -2 weeks prior

- Send reminder emails to attorneys, parties, and mediators.

- Provide any updated information to Judges, Magistrates and Court Administrators

☐ 	Finalize Staff Assignments – 1 -2 weeks prior

- Assign staff for check in location

- Assign staff for mediator, attorney, and party support (as needed)

- Assign staff for any other tasks (as needed)

☐ 	Finalize Documents – 1 week prior

- Create check-in sheets for all mediation cases

- Create conference room reserved signs for applicable days/times

- Create any entranceway or directional signs

- Stuff folders with welcome sheets and organize folders in week order

- Check all spreadsheets and remedy any remaining scheduling issues

☐ 	Set Up – 1 day prior

- Hang-up room number & conference room reserved signs

- Stock conference rooms w/ supplies